## Project
Total Project Tracking
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Home page | Public | Admin, Manager | - Show navigation bar:Home,Ranking,Class,Payment,Setting,Profile,Support Center -Show the newest information which are about notification of courses,update news about education,change of the web,premium account,… -Show the advertisement of course in web | Hoàng | Done | iter1 | iter2 | FE:Done
2 | Pop-Up | Public | Guest,User | Show the notification to user | Hoàng | Done | iter2 | none | FE: Done
3 | Class | Common | Guest,User | Show navigation bar:Home,Ranking,Class,Payment,Setting,Profile,Support Center -Show all of the class from grade 1 to grade 5 -User can choose the suitable class that they want to learn | Khang | Done | iter2 | none | FE:Done
5 | Course | Public | Guest,User | Show navigation bar:Home,Ranking,Class,Payment,Setting,Profile,Support Center -Show all of the course of the class (Maths,Literature,English) -User can choose one of three subjects to learn | Khang | Done | iter1 | none | FE:Done
6 | Chapter | Common |  | - Show na | Khang | Done | iter2 | none | FE:Done
6 | Payment | Public | Guest,User | Show navigation bar:Home,Ranking,Class,Payment,Setting,Profile,Support Center -Show feature of normal account and premium account -User can choose to register normal or premium account | Thắng | Done | iter2 | none | FE: Done
7 | Payment page | Public | Guest,User | Show navigation bar:Home,Ranking,Class,Payment,Setting,Profile,Support Center -Show the payment method and premium account detail -User will fill the information of credit card(number of card,date,pass) | Thắng | Done | iter2 | none | FE:Done
8 | Support center | Public | User | User can ask question via email, phone or send messages | Thắng | to do | iter3 | iter4 | Delete
9 | User Login | Common | User | This screen allows user to login with username, after login user redirect to Home page | Kiên | Done | iter2 | none | FE: Done and BE: Done
10 | User Register | Common | User | This screen allow user to regist their account by fill the username,password and repassword -User should create account in the right way | Kiên | Done | iter2 | none | FE: Done and BE: Done
11 | Setting | Common | User | Show navigation bar:Home,Ranking,Class,Payment,Setting,Profile,Support Center -User can change the audio, change password and log out account | Hoàng | to do | iter3 | none | Delete
12 | Module | Common | User | Show all lesson of the module of the subject , user can choose lesson to learn | Khang | Done | iter2 | none | FE: Done and BE: Done
13 | Progress | Common | User | Show the progress percent user do in the subject. | Khang | Done | iter1 | none | Delete
14 | Lession | Common | User | Show the lecture of the subject(include game,quiz,video) for user to do. | Khánh | Done | iter1 | none | FE: Done
15 | Ranking | Common | User | Show the ranking point of subject (sort to subject). | Hoàng | Done | iter2 | none | FE: Done
17 | Payment completion | Common | User | This screen notifies to user that user have completely signed up premium account. | Thắng | Done | iter2 | none | FE: Done
18 | Register user | Admin | Admin | Admin mange account user via this page . | Khánh | to do | iter3
19 | User profile | Common | User | This screen allows user to edit his/her profile information(include full name,email,phone number,address). | Hoàng | to do | iter3 |  | FE: Done and BE: To do
20 | Games | Common | User | User can play game to learn the lesson and get their point via playing game. | Khánh | Done | iter2 | none | FE: Done and BE: Done
21 | Confirm sign up | Common | User | This screen show the bar code that you need to login to your email and fill the right code we send to your email to finish sign up. | Kiên | Done | iter3 | none | FE: Done
22 | Fail payment | Common | User | This screen notifies to user that user have failed to pay. User can choose try again or cancel. | Thắng | Done | iter3 | none | FE: Done
23 | Email payment | Common | User | This screen notifies to user that user have to fill email to confirm to pay. User need to fill their email address and click to send code to pay. | Khang | Done | iter3 | none | FE: Done
24 | Cofirm payment | Common | User | This screen notifies to user to enter code which have 6 numbers. The code is in their email that we sent to. User need to fill the code in 2 minutes or the code will be expired. | Thắng | Done | iter4 | none | FE: Done
25 | Manage quiz | Admin | Admin | - Show form which admin choose class, course, chapter, lession that admin want to add or delete quiz. - After fill the form, admin press “Hoàn Tất” to add quiz. - After choose question, admin press “Xác nhận và xóa” to delete quiz. | Thắng | Done | iter4 | none | FE: Done
26 | Manage games | Admin | Admin | - Show form which admin choose class, course, chapter, lession that admin want to add pictures for game. - After fill the form, admin press “Hoàn tất” to add pictures. | Thắng | Done | iter4 | none | FE: Done
27 | Manage video lession | Admin | Admin | - Show form which admin choose class, course, chapter, lession that admin want to add video lession. - After fill the form, admin press “Hoàn tất” to add video lession. | Thắng | Done | iter4 | none | FE: Done;BE:Done
28 | Manage content | Admin | Admin | - Show form which admin choose class, course, chapter, lession that admin want to add/edit content. - After fill the form, admin press “Hoàn tất” to add content or edit content. | Thắng | Done | iter4 | none | FE: Done;BE:Done
29 | Manage user | Admin | Admin | - Show total account which include normal account and premium account. - Show list of account information which include: Full name, date of birth, gender, parent’s full name, parent’s email, parent’s phone number and usernamme. - Admin can search by name account. | Thắng | Done | iter4 | none | FE: Done;BE:Done
30 | Add/modify chapter | Admin | Admin | - Show form which admin choose class, course, chapter that admin want to add or modify chapter. - After fill the form, admin press “Hoàn tất” to add or modify chapter. | Thắng | Done | iter4 | none | FE: Done;BE:Done
31 | Add/modify lesson | Admin | Admin | - Show form which admin choose class, course, chapter that admin want to add or modify module. - After fill the form, admin press “Hoàn tất” to add or modify module. | Thắng | Done | iter4 | none | FE: Done;BE:Done

## Iter1
Iteration Tracking - Iteration 1
# | Screen/Function | Feature | Screen/Function Description | In Chargre | Status | Notes
1 | Home page | Public | Show navigation bar: Home, ranking, class, payment, setting, profile, support center. Show the newest information which are about notification of courses, update news about education, change of the web, premium account, etc. Show the advertisement of course in web. | Hoàng | Done
2 | Progress | Common | This screen show the progress percent user have learnt. | Khang | Done
3 | Lesson | Common | This screen show the content(include video) and exercise(include quiz, games). | Khánh | Done
4 | Course | Public | Show navigation bar:Home,Ranking,Class,Payment,Setting,Profile,Support Center Show all of the course of the class (Maths,Literature,English) User can choose one of three subjects to learn. | Khang | Done

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | Notes
1 | Class | Public | Show navigation bar:Home,Ranking,Class,Payment,Setting,Profile,Support Center Show all of the class from grade 1 to grade 5 User can choose the suitable class that they want to learn | Khang | Done
2 | Payment | Public | Show navigation bar: Home, Ranking, class, payment, setting, profile, support center. Show feature of normal account and premium account. User can choose to register normal or premium account. | Thắng | Done
3 | Payment page | Public | Show navigation bar: Home, ranking, class, payment,setting, profile, support center. Show the payment method and premium account detail. User will fill the information of credit card(number of card,date,pass). | Thắng | Done
4 | User login | Common | This screen allows user to login with username, after login user redirect to Home page. | Kiên | Done
5 | User register | Common | This screen allow user to regist their account by fill the username,password and repassword. User should create account in the right way. | Kiên | Done
6 | Module | Common | Show all lesson of the module of the subject , user can choose lesson to learn. | Khang | Done
7 | Ranking | Common | Show the ranking point of subject (sort to subject) . | Hoàng | Done
8 | Payment Completion | Common | This screen notifies to user that user have completely signed up premium account. User can click to back to Home Page. | Thắng | Done
9 | Games | Common | User can play game to learn the lesson and get their point via playing game. | Khánh | Done
10 | Pop-up | Public | Show the notification to user. | Hoàng | Done

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | Notes
1 | Quiz | Common | User can do quiz to revise lesson and get point. | Khánh | Done | BE:Done
2 | User profile | Common | This screen allow user to regist their account by fill the username, password and repassword. User should create account in the right way. | Hoàng | Done | BE:Done
3 | Edit profile | Common | You can change your profile on this screen. | Hoàng | Done | BE:Done
4 | Confirm sign up | Common | This screen show the bar code that you need to login to your email and fill the right code we send to your email to finish sign up. | Kiên | Done | BE:Done
5 | Fail payment | Common | This screen notifies to user that user have failed to pay. User can choose try again or cancel. | Thắng | Done | BE:Done
6 | Email payment | Common | This screen notifies to user that user have to fill email to confirm to pay. User need to fill their email address and click to send code to pay. | Khang | Done | BE:Done
7 | Confirm payment | Common | This screen notifies to user to enter code which have 6 numbers. The code is in their email that we sent to. User need to fill the code in 2 minutes or the code will be expired. | Khang | Done | BE:Done
8 | Video lesson | Common | This screen show the video lesson for user to learn . | Khang | Done | BE:Done

## Iter4
Iteration Tracking - Iteration 4
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | Notes
1 | Manage quiz | Admin | User can do quiz to revise lesson and get point. | Khánh | Done | BE:Done; Fe:Done
2 | Manage games | Admin | This screen allow user to regist their account by fill the username, password and repassword. User should create account in the right way. | Khánh | Done | BE:Done; Fe:Done
3 | Manage video lession | Admin | You can change your profile on this screen. | Hoàng | Done | BE:Done; Fe:Done
4 | Manage content | Admin | This screen show the bar code that you need to login to your email and fill the right code we send to your email to finish sign up. | Kiên | Done | BE:Done; Fe:Done
5 | Manage user | Admin | This screen notifies to user that user have failed to pay. User can choose try again or cancel. | Thắng | Done | BE:Done; Fe:Done
6 | Add/modify chapter | Admin | This screen notifies to user that user have to fill email to confirm to pay. User need to fill their email address and click to send code to pay. | Khang | Done | BE:Done; Fe:Done
7 | Add/modify lession | Admin | This screen notifies to user to enter code which have 6 numbers. The code is in their email that we sent to. User need to fill the code in 2 minutes or the code will be expired. | Khang | Done | BE:Done; Fe:Done