## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Home Page | Public | Admin, Manager | Show navigation bar:Home,Ranking,Class,Payment,Setting,Profile,Support Center -Show the newest information which are about notification of courses,update news about education,change of the web,premium account,… -Show the advertisement of course in web | Hoàng | Done | iter1 | iter2 | Front End
2 | Pop-Up | Public | Guest,User | Show the notification to user | Hoàng | Done | iter2 | none | Front End
3 | News | Public | Guest,User | Show navigation bar:Home,Ranking,Class,Payment,Setting,Profile,Support Center -Show the detail of the news to the user -Show the advertisement of course in web | Hoàng | Doing | iter3 | none | Back End
4 | Class | Public | Guest,User | Show navigation bar:Home,Ranking,Class,Payment,Setting,Profile,Support Center -Show all of the class from grade 1 to grade 5 -User can choose the suitable class that they want to learn | Khang | Done | iter2 | none | Front End
5 | Course | Public | Guest,User | Show navigation bar:Home,Ranking,Class,Payment,Setting,Profile,Support Center -Show all of the course of the class (Maths,Literature,English) -User can choose one of three subjects to learn | Khang | Done | iter1 | none | Front End + Back End
6 | Payment | Public | Guest,User | Show navigation bar:Home,Ranking,Class,Payment,Setting,Profile,Support Center -Show feature of normal account and premium account -User can choose to register normal or premium account | Thắng | Done | iter2 | none | Front End + Back End
7 | Payment Page | Public | Guest,User | Show navigation bar:Home,Ranking,Class,Payment,Setting,Profile,Support Center -Show the payment method and premium account detail -User will fill the information of credit card(number of card,date,pass) | Thắng | Done | iter2 | none
8 | Support Center | Public | User | User can ask question via email, phone or send messages | Thắng | to do | iter3
9 | User Login | Common | User | This screen allows user to login with username, after login user redirect to Home page | Kiên | Done | iter2 | none
10 | User Register | Common | User | This screen allow user to regist their account by fill the username,password and repassword -User should create account in the right way | Kiên | Done | iter2 | none
11 | Setting | Common | User | Show navigation bar:Home,Ranking,Class,Payment,Setting,Profile,Support Center -User can change the audio, change password and log out account | Hoàng | to do | iter3
12 | Module | Common | User | Show all lesson of the module of the subject , user can choose lesson to learn | Khang | Done | iter2 | none
13 | Progress | Common | User | Show the progress percent user do in the subject | Khang | Done | iter1 | none
14 | Lesson | Common | User | Show the lecture of the subject(include game,quiz,video) for user to do | Khánh | Done | iter1 | none
15 | Ranking | Common | User | Show the ranking point of subject (sort to subject) | Hoàng | Done | iter2 | none
17 | Payment Completion | Common | User | This screen notifies to user that user have completely signed up premium account | Thắng | Done | iter2 | none
18 | Register User | Admin | Admin | Admin mange account user via this page | Khánh | to do | iter3
19 | User Profile | Common | User | This screen allows user to edit his/her profile information(include full name,email,phone number,address) | Hoàng | to do | iter3
20 | Games | Common | User | user can play game to learn the lesson and get their point via playing game | Khánh | Done | iter2 | none

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Home Page | Public | This is short descripiton for the screen/function (2-3 sentences) | Hoàng | Done |  | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document